## Test summary
SQA Test Summary |  |  |  |  | JIRA | Status | Notes | Firmware
Reader: | VP8800 |  |  |  | PSH-1000 - r26188 - (DVT) Get Signature (83-02) does not return to "Welcome" after signature is complete | New - Unresolved | Assigned to Jeff
HW model/Ver: | IDPP-1881D Rev B (From Shane) |  |  |  | PSH-998 - Get Online Enciphered PIN (83-43) --> response is not as expected | Refer to PSH-996 | Jeff said not a bug,
FW build: | KH0 AR 3.0.0.D r26188
BL build: | 1.0.2
Start on: | 2020-05-04 |  |  |  | PSH-989 - r26188 - (DVT) DFEE58 Secondary Language returns with error status. | Fixed - Verify on next fw
End on: |  |  |  |  | PSH-926 - r26024 - ACT (02-05) - Fallback from Contact (ICC) Interface - Returns with "0A" error after swiping card. | Fixed- Verify on next IDG | Check next available IDG
AR IDG rev. | AR 3.0.0 IDG rev.109
NGAT ver. : | NGAT V1.10.XX |  |  |  | For Kate, Would you check Pass-Thru, Secure Pass-Thru and UI Tabs and run those hightlighted tests?
Test category | Assigner | Estimated test time (Hr) | % of completeness | Note | Fixed/Closed Jira Issues
CAPK | Duc | na | 100% - All Pass | 6 | PSH-997 -(DVT) Display buttons response not responding. | Not a bug - Closed
Config | Duc | na | 100% - See failed test | 48 | PSH-991 - (DVT) - Activate Transaction results in immediate "0C" error. | Fixed and Closed
Contactless | - | na | Skip, Tab hidden | 0 | PSH-983 - VP8800: IDPP-1881D-RevB- r26185 - (DVT) Reader losses communication after contact transaction. | Fixed and Closed | Observed on r26188
Diagnostic | Duc | na | 100% - All Pass | 7 | PSH-970 - Reader should point out which TLV that has problem when returning error status code in setting configurable parameters | Fixed and Closed | Verified on r26185
EMV-CMD | Duc | na | 100% - All Pass | 2 | PSH-969 - Display Image (83-0E) Coordinate (0,0) 100x100 - Reader is expected to return status code 0x00 instead of 0x0A. | Fixed and Closed | See comments in JIRA
Event | Duc | na | 100% - All Pass | 8 | PSH-954 - 2C-11 Enhanced Pass Through for display second string returns with status code 05 instead of 00 | Not a bug/Closed | Modified script to display correct 2nd string.
Pass-Thru | Duc | na | 100% - See Fail issues | 21 | PSH-958 - Out of Screen Coordinate [500,500] - Expecting: Return error code "05" instead of "0A" | Closed - Wont Fix
Secure Passthrough | Duc | na | 100% - See Fail issues | 1 | PSH-937 - r26024 - Reader Secondary Language Changed to Spanish after inserting qVSDC contact card | Fixed and Closed | Verified on r26134 | Pass on r26185
Transaction | Duc | na | 100% - See tab | 23 | PSH-934 - r26024 - "Welcome" msg stays on LCD during activate transaction. | Fixed and Closed | Verified on r26134
UI | Duc | na | 100% - See Fail issues | 69 | PSH-933 - r26024 - Activate Transaction for Contactless ONLY shows "Tap, Insert or swipe card", Expecting LCD to show "Please Present Card" only. | Fixed and Closed | Verified on r26134
TS | - | na | Skip, Tab hidden |  | PSH-931 - r26024 - "Transaction Cancelled" msg appears twice after canceling transaction for contact transaction. | Fixed and Closed | Verified on r26134
SDK | - | na | Skip, Tab hidden |  | PSH-930 - Activate Transaction - Enable 3 interface, can not read contact card. | Resolved and Closed | Not a bug
|  | 0 |  |  | PSH-921 - r26002 - Activate Transaction - Contact card returns IDT address in 9F4E | Fixed and Closed | Verified on r26134
| Working day: | 0 |  | 185 | PSH-893 - r26002 - Set Reader Second Language DFEE58 = 20 20 (Hex) to Default returns with error "05" | Fixed and Closed | Verified on r26134
[5 empty] | PSH-900 - Returns "0C" expecting to return "00" for a valid date. | Resolved and Closed | Not a bug: IDG command 25-05 cannot be used in secure mode. In Secure Mode, use SMFG Set UTC (91-01) or SMSG Set UTC (93-05) instead.
[5 empty] | PSH-899 - Mastercard Module missing from Get Version. | Resolved and Closed | Not a bug
[5 empty] | PSH-893 - Default returns with error "05" | Fixed and Closed | Verified on r26134
[5 empty] | PSH-891 - Response returns incorrect format. | Fixed and Closed | Fix on r26024
[5 empty] | PSH-890 - Debug enabled in this build expected? | Fixed and Closed | Check next available build, Fix on r26024
[5 empty] | PSH-886 - Disable ViVOpay default Buzzer UI, Buzzer is still heard. | Resolved | Closed
[5 empty] | PSH-885 - Command shows error code "05" but command turns on ALL LEDs. | Fixed and Closed | Check next available build, Fix on r26024
[5 empty] | PSH-880 - AT then Swipe card, LCD is blank then goes back to "Welcome" message. | Resolved | Closed, Not a bug. See
Note on G15: Duc: PSH-893 - Fixed and Closed, Pass on r26024

## CAPK
| Summary |  |  |  | Summary
| Pass | 6 | 100% |  | Scripted
| FAIL | 0 | 0% |  | Not Scripted
| Not Performed |  | 0% |  | Total
| Not Supported | 0 | 0%
| Total | 6 | 100%
Part | Title | Title No. | Case No./Name | Description | Test result | Duc Notes
CAPK | Set CA Public Keys | 01SetCAPK | 1SetCAPK_CTLS_D0-23 | Set CAPK, CTL | Pass | All tests pass on r26188
|  |  | 2SetCAPK_CT_D0-23 | Set CAPK, CT | Pass | All tests pass on r26188
|  |  | 3SetCAPK_Both_D0-23 | Set CAPK, CT & CTL | Pass | All tests pass on r26188
| Get CA Public Keys | 02GetCAPK | 1GetCAPK_D0-22,27 | Get CAPK, Hash, RIDs, Indices for RID | Pass | All tests pass on r26188, Set Protocol to: VIV, in configuration setting in NGAT
| Delete CA Public Keys | 03DeleteCAPK | 1DeleteCAPK_D0-24 | Delete CAPK | Pass | All tests pass on r26185
|  |  | 2DeleteAllCAPK_D0-25 | Delete all CAPK | Pass | All tests pass on r26185, rerun single tests again if failing on first run.

## Config
Part | Title | Title No. | Case No./Name | Description | Test result | Note | JIRA | Duc's Comments
Config | Buzzer, LED | 01BuzzerLED | 1BuzzerLED_Buzzer_01-02 | Beep | Pass |  |  | All tests pass on r26188
|  |  | 2BuzzerLED_LED_01-02 | LED | Pass |  | PSH-885 - Fixed and Closed | All tests pass on r26188
| Source for LCD, Buzzer, LED | 02SourceForLCDBuzzerLED | 1SourceIndicator_Buzzer_01-05 | Buzzer | N/A | Replace by test case 1SourceIndicator_Buzzer_01-05_TW |  | All tests pass on r26188
|  |  | 2SourceIndicator_LCDText_01-05 | LCD, ViVOpay default text | N/A | Replace by test case 2SourceIndicator_LCDText_01-05_TW |  | All tests pass on r26188
|  |  | 3SourceIndicator_LCDTrans_01-05 | LCD, Transaction type | N/A | Replace by test case 3SourceIndicator_LCDTrans_01-05_TW |  | All tests pass on r26188
|  |  | 4SourceIndicator_LED_01-05 | LED | N/A | Replace by test case 4SourceIndicator_LED_01-05_TW |  | All tests pass on r26188
|  |  | 5SourceIndicator_LCDLogo_01-05 | LCD Contactless logo | N/A | Replace by test case 5SourceIndicator_LCDLogo_01-05_TW |  | All tests pass on r26188
|  |  | 1SourceIndicator_Buzzer_01-05_TW | Buzzer | Pass | Modified script to disabled Buzzer UI - 03 00 14 00 | PSH-886 - Not a bug. See comments - Closed | All tests pass on r26188
|  |  | 2SourceIndicator_LCDText_01-05_TW | LCD, ViVOpay default text | Pass | Modified script to disabled default MSG UI - 03 00 11 00 |  | All tests pass on r26188
|  |  | 3SourceIndicator_LCDTrans_01-05_TW | LCD, Transaction type | Pass | Added 9C to Activate Transaction for default transaction type. | PSH-870 - See Comments from Kate's Issue | All tests pass on r26188
|  |  | 4SourceIndicator_LED_01-05_TW | LED | Pass | All tests passes |  | All tests pass on r26188
|  |  | 5SourceIndicator_LCDLogo_01-05_TW | LCD Contactless logo | Pass | Modify Script to Disable Contactless Logo UI – 03 00 18 00 |  | All tests pass on r26188
| System Configuration | 03SystemConfiguration | 14SysConfig_MaskDataDFEE1D_04-01,03-02 | Configuration for Masking Sensitive Data (DFEE1D) | Pass | Replace by 14SysConfig_MaskDataDFEE1D_04-01,03-02_TW |  | All tests pass on r26188
|  |  | 14SysConfig_MaskDataDFEE1D_04-01,03-02_TW | Configuration for Masking Sensitive Data (DFEE1D) | Pass | Load Data encryption key and PIN key |  | See video to load keys - on r26134
|  |  | 16SysConfig_LangOptLCDDFEE38_04-01,03-02 | Language Option for LCD display (DFEE38) | Pass | Modify script now Passes | PSH-891 - response returns incorrect format. Enhancement, | All tests pass on r26188
|  |  | 17SysConfig_AppCapabilityDFEE44_04-01,03-02 | Application Capability (DFEE44) | N/A | Replace by 17SysConfig_AppCapabilityDFEE44_04-01,03-02_TW
|  |  | 17SysConfig_AppCapabilityDFEE44_04-01,03-02_TW | Application Capability (DFEE44) | Pass | Modify script now Passes, Default DFEE44=B5 FF, Script Shows FF FF, |  | All tests pass on r26188
|  |  | 19SysConfig_PriLangDFEE57_04-01,03-02 | Reader Primary Language(DFEE57) | Pass | Modify script now passes, returns correct error response | PSH-891 - Fixed and Closed. | All tests pass on r26188
|  |  | 20SysConfig_SecLangDFEE58_04-01,03-02 | Reader Secondary Language(DFEE58) | Fail | Set fr, es, en, can not be set for DFEE58, Can be set for DFEE57 - CHECK! r26188 | PSH-989 - Fixed | Check next available build
|  |  | 21SysConfig_EnableStopCmdDFEE68_04-01,03-02 | Stop Command Processing Enable(DFEE68) | Pass | Set 02 (Invalid), now correct with modified script. | PSH-891 - Fixed and Closed | All tests pass on r26188
|  |  | 25SysConfig_COMTimeoutDFEE7B_04-01,03-02 | Serial Communications Timeout value (DFEE7B) | N/A | Test script without pass criteria
|  |  | 27SysConfig_HeartbeatDFEF72_04-01,03-02 | Heartbeat Enable (DFEF2A) | Pass | All 4 tests passes, Fixed script for invalid response. |  | All tests pass on r26188
|  |  | 28SysConfig_WatchdogPeriodDFEF35_04-01,03-02 | Communications Watchdog Period(DFEF35) | Skip | Not to run w/ this script
|  |  | 29SysConfig_TimeZoneDFEF43_04-01,03-02 | Time Zone and Daylight Savings Information(DFEF43) | Pass | All 7 tests passes |  | All tests pass on r26188
|  |  | 30SysConfig_PrepollMechCtlDFEF72_04-01,03-02 | Pre-poll card mechanism control(DFEF72) | Pass | Modified script to return correct format for error response. | PSH-891 - Fixed and Closed | All tests pass on r26188
|  |  | 31SysConfig_PINFormatDFEF79_04-01,03-02 | PIN block format (when TDES)(DFEF79) | N/A | NO test procedure
| Terminal Data | 06EMVTerminal | FWC00601 | 9F33,Terminal Capabilities | Pass | FWC00601 - Fixed Script. Set 60F8C8 Default for 9F33 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00602 | 9F35,Terminal Type | Pass | FWC00602 - Fixed Script. Set 22 Default for 9F35 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00603 | 9F40,Additional Terminal Capabilities | Pass | Replace by test case FWC00603_TW | PSH-893 - Fixed and Closed | All tests pass on r26134
|  |  | FWC00603_TW |  | Pass | FWC00603 - Fixed Script. Set F000F0A001 Default for 9F40 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00604 | DFEE11,Transaction Log Support | Pass | FWC00604 - Fixed Script. Set 01 Default for DFEE11 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00605_TW | DFEE0F,Revocation List Support | Pass | FWC00605_TW - Fixed Script. Set 01 Default for DFEE0F | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00606 | DFEE3E,Exception File Support | Pass | FWC00606 - Fixed Script. Set 00 Default for DFEE3E | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00607 | DFEE1E,Contact Terminal Configuration | Pass | FWC00607 - Fixed Script. Set F0DC3CF0C29E9600 Default for DFEE1E | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00608 | 5F36,Transaction Currency Exponent | Pass | FWC00608 - Fixed Script. Set 02 Default for 5F36 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00609 | 9F1A,Terminal Country | Pass | FWC00609 - Fixed Script. Set 0840 Default for 9F1A | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00610 | 9F1E,Interface Device Serial Number | Pass | FWC00610 - Fixed Script. Set 5465726D696E616C Default for 9F1E | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00611 | 9F15,Merchant Code | Pass | FWC00611 - Fixed Script. Set 1234 Default for 9F15 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00612 | 9F16,Merchant Identifier | Pass | FWC00612 - Fixed Script. Set Default for 9F16 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00613 | 9F1C,Terminal Identification | Pass | FWC00613 - Fixed Script. Set Default for 9F1C | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00614 | 9F4E,Merchant Name and Location | Pass | FWC00614 - Fixed Script. Set Default for 9F4E | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00615 | DFEE10,Language | Pass | FWC00615 - Fixed Script. Set Default for DFEE10 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00616 | DFEE15,Application Selection Indicator | Pass | FWC00616 - Fixed Script. Set Default for DFEE15 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00617 | DFEE16,DUKPT or MK/SK Select for online PIN encrypted | Pass | FWC00617 - Fixed Script. Set Default for DFEE16 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00618 | DFEE17,ICC Entry Mode | Pass | FWC00618 - Fixed Script. Set Default for DFEE17 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00619 | DFEE18,Terminal Encrypt Mode for MSR | Pass | FWC00619 - Fixed Script. Set Default for DFEE18 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00620 | DFEE1F,Issuer script device limit | Pass | FWC00620 - Fixed Script. Set Default for DFEE19 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00621 | DFEE1B,Authorization Response Code | Pass | FWC00621 - Fixed Script. Set Default for DFEE1B | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00622 | DFEE20,ICC Power on detect waiting time | Pass | FWC00622 - Fixed Script. Set Default for DFEE20 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00623 | DFEE21,ICC L1 waiting time | Pass | FWC00623 - Fixed Script. Set Default for DFEE21 | PSH-893 - Fixed and Closed | All tests pass on r26188
|  |  | FWC00624 | DFEE22,Driver Timeout | Pass | FWC00624 - Fixed Script. Set Default for DFEE22 | PSH-893 - Fixed and Closed | All tests pass on r26188
| Baud Rate | 09BaudRate | FWC00901 | Set baud rate command validity | Pass | Not to run w/ this script
| VP8800 LED Commands | 10LED | FWC01001 | Tri-color MSR LED Control | Pass | All tests passes |  | All tests pass on r26188
|  |  | FWC01002 | ICC LED Control | Pass | All tests passes |  | All tests pass on r26188
|  |  | FWC01003 | KEYPAD Backlight Control | Pass | All tests passes |  | All tests pass on r26188
| Network Commands | 11Network | FWC01101 | Ethernet MAC Address | Pass | All tests passes |  | All tests pass on r26188
|  |  | FWC01102 | Network Configuration | Fail | 3 tests fail w USB Connection, See screenshot below, Modified script for error response | Investigate | 3 Test fail on r26188
| UTC Date and Time | 12UTC | FWC01201 | UTC date, non-secure mode | Pass | Fixed scripts | PSH-900 - Returns "0C" - Not a bug. See Note, observed on r26024 | All tests pass on r26188
|  |  | FWC01202 | UTC time, non-secure mode | Pass | Use SMFG set uTC (91-01_ or SMGS Set UTC (93-05) Instead, Per JIRA, Need to modify scripts | PSH-900 - Returns "0C" - Not a bug. See Note, observed on r26025 | All tests pass on r26188
| Configure External Module UI Events | 13ExternalModuleUIEvents | FWC01301 | Configure External Module UI Events | Skip | Not to run w/ this script
FWC01102 - Network Configuration
Note on H20: Duc: PSH-893 - Fixed and Closed, Pass on r26024 PSH-970 - Fixed and Closed
Note on G35: Duc: 1 failed. Per IDG, VP8800 always uses 1C as default configuration and disallows to change both major and minor parameter. Modified script to add return status code 05 for any tag changed in 1C, which is not allowed .PSH-724
Note on G42: Duc: Refer to PSH-921, Changed script to return 9F4E 00
Note on G53: Duc: Passed
Note on C54: Duc: Automatic Pass
Note on G58: Duc: April 8th 2020 Skype Hi Duc, PSH-958 is ok (not an issue). 0a shows a fail in general and the extended error code shows 0000 0007, which indicates Out of boundary error. The test script can be updated accordingly.
Note on G59: Duc: Use SMFG set uTC (91-01_ or SMGS Set UTC (93-05) Instead, Per JIRA, Need to modify scripts
Note on I59: Duc: Passes with same script on r26024, per PSH-900, 25-05 can not be set in secure mode per IDG pg 44, Investigate
Note on I60: Duc: Passes with same script on r26024, per PSH-900, 25-05 can not be set in secure mode per IDG pg 44, Investigate

## Contactless (hidden)
Project | Title No. | Test case | Description | Test card | Test result | Note
Contactless | ACT-SECURE | ACT-0S | Wrong CRC & Can't use in PT(0B) & tag length≠real length of value |  | Skip
|  | ACT-1S | Test time out & 02-01,02-20,02-11 can't be used in secure mode |  | Skip
|  | ACT-2S | Test cancel command (05-01) |  | Skip
|  | ACT-3S |  | qVSDC | Skip
|  | ACT-4S | Event mode for 02-05 |  | Skip
|  | ACT-5S | 9F02, 5F2A, 9F1A, 9C, 5F36 |  | Skip
|  | ACT-6S.0 | Test DFEE1D value invalide |  | Skip
|  | ACT-6S.1 | Test output, encryption, DFEE1D-06042A0C31 (with slot0) | All cards | N/A | Replace by ACT-6S.1-1_TW~ACT-6S.1-7_TW
|  | ACT-6S.1-1_TW | Test output, encryption, DFEE1D-06042A0C31 (with slot0) | Master NO3 card | Skip
|  | ACT-6S.1-2_TW | Test output, encryption, DFEE1D-06042A0C31 (with slot0) | qVSDC 32 card (Type A) | Skip
|  | ACT-6S.1-3_TW | Test output, encryption, DFEE1D-06042A0C31 (with slot0) | XP2 NO6 Card | Skip
|  | ACT-6S.1-4_TW | Test output, encryption, DFEE1D-06042A0C31 (with slot0) | MCHIP NO2 | Skip
|  | ACT-6S.1-5_TW | Test output, encryption, DFEE1D-06042A0C31 (with slot0) | qVSDC 36 Card (Type B) | Skip
|  | ACT-6S.1-6_TW | Test output, encryption, DFEE1D-06042A0C31 (with slot0) | Interac NO2 Card | Skip
|  | ACT-6S.1-7_TW | Test output, encryption, DFEE1D-06042A0C31 (with slot0) | Discover Card | Skip
|  | ACT-6S.2 | Test output, encryption, DFEE1D-00002A0B30 (Slot0,only CL on | All cards | N/A | Replace by ACT-6S.2-1_TW~ACT-6S.2-7_TW
|  | ACT-6S.2-1_TW | Test output, encryption, DFEE1D-00002A0B30 (Slot0,only CL on | Master NO3 card | Skip
|  | ACT-6S.2-2_TW | Test output, encryption, DFEE1D-00002A0B30 (Slot0,only CL on | qVSDC 32 card (Type A) | Skip
|  | ACT-6S.2-3_TW | Test output, encryption, DFEE1D-00002A0B30 (Slot0,only CL on | XP2 NO6 Card | Skip
|  | ACT-6S.2-4_TW | Test output, encryption, DFEE1D-00002A0B30 (Slot0,only CL on | MCHIP NO2 | Skip
|  | ACT-6S.2-5_TW | Test output, encryption, DFEE1D-00002A0B30 (Slot0,only CL on | qVSDC 36 Card (Type B) | Skip
|  | ACT-6S.2-6_TW | Test output, encryption, DFEE1D-00002A0B30 (Slot0,only CL on | Interac NO2 Card | Skip
|  | ACT-6S.2-7_TW | Test output, encryption, DFEE1D-00002A0B30 (Slot0,only CL on | Discover Card | Skip
|  | ACT-6S.3 | Test output, encryption, DFEE1D-06042A0C30 (with slot1) | All cards | N/A | Replace by ACT-6S.3-1_TW~ACT-6S.3-7_TW
|  | ACT-6S.3-1_TW | Test output, encryption, DFEE1D-06042A0C30 (with slot1) | Master NO3 card | Skip
|  | ACT-6S.3-2_TW | Test output, encryption, DFEE1D-06042A0C30 (with slot1) | qVSDC 32 card (Type A) | Skip
|  | ACT-6S.3-3_TW | Test output, encryption, DFEE1D-06042A0C30 (with slot1) | XP2 NO6 Card | Skip
|  | ACT-6S.3-4_TW | Test output, encryption, DFEE1D-06042A0C30 (with slot1) | MCHIP NO2 | Skip
|  | ACT-6S.3-5_TW | Test output, encryption, DFEE1D-06042A0C30 (with slot1) | qVSDC 36 Card (Type B) | Skip
|  | ACT-6S.3-6_TW | Test output, encryption, DFEE1D-06042A0C30 (with slot1) | Interac NO2 Card | Skip
|  | ACT-6S.3-7_TW | Test output, encryption, DFEE1D-06042A0C30 (with slot1) | Discover Card | Skip
|  | ACT-6S.4 | Select data DUKPT Key slot 0~9 to test encryption | qVSDC N.36 | Skip
|  | ACT-7S-all other bits | DFEE44 all other bits | All CL cards | Skip
|  | ACT-7S-B1b3 | DFEE44 B1b3 | All CL cards | Skip
|  | ACT-7S-B2b1 | DFEE44 B2b1 | All CL cards | Skip
|  | ACT-7S-B2b2 | DFEE44 B2b2 AMEX | All CL cards | Skip
|  | ACT-7S-B2b3 | DFEE44 B2b3 VISA | All CL cards | Skip
|  | ACT-7S-B2b7 | DFEE44 B2b7 | All CL cards | N/A
|  | ACT-7S-B2b8 | DFEE44 B2b8 | All CL cards | Skip
|  | ACT-8S-fail to MSR | DFEE79, DFEE7A, DFEE4E | qVSDC typeB | Skip
|  | ACT-8S-fail to PT |  |  | Skip
|  | ACT-9S |  |  | Skip
| AID | AID-0 | With wrong CRC(04) & Can't use in PT(0B) |  | Skip
|  | AID-1 | 9F06, DFEE2D |  | Skip
|  | AID-2 | DFEE2E |  | Skip
|  | AID-3 |  |  | Skip
|  | AID-4.1 | DFEE2F, DFEE4B, DFEE4C, DFEE4F | Amex | Skip
|  | AID-4.2 |  | Master | Skip
|  | AID-4.3 |  | VISA qVSDC | Skip
|  | AID-4.4 |  | DiscoverZIP | Skip
|  | AID-4.5 |  | Interac | Skip
|  | AID-5 | DFEE4A, DFEE4C |  | Skip
|  | AID-6.1 | DFEE4D(API required) | qVSDC 38 (CLQD.005.03) | Skip
|  | AID-6.2 | DFEE54, DFEE4D | VISA qVSDC | Skip
|  | AID-7 | DFEE4F |  | Skip
|  | AID-8.0 | DFEE2F & Delete AID |  | Skip
|  | AID-8.1 |  | Amex | Skip
|  | AID-8.2 |  | Master | Skip
|  | AID-8.3 |  | VISA qVSDC | Skip
|  | AID-8.4 |  | DiscoverZIP | Skip
|  | AID-8.5 |  | Interac | Skip
|  | AID-9 | Default all & check default AIDs |  | Skip
| Apple VAS | applepay1-1 |  |  | N/A | Replace by test case applepay1-1_TW
|  | applepay1-2 |  |  | N/A | Replace by test case applepay1-2_TW
|  | applepay1-3 |  |  | N/A | Replace by test case applepay1-3_TW
|  | applepay1-4 |  |  | N/A | "IDTECH ENCRYPTION NO card" is not available
|  | applepay1-5 |  |  | N/A | Replace by test case applepay1-5_TW
|  | applepay1-6 |  |  | N/A | "Unencrypted Rewards card" is not available
|  | applepay1-7 |  |  | Skip
|  | applepay2-0 | Set merchant ID1 for IDTECH cards |  | Skip
|  | applepay2-1 |  |  | N/A | Replace by test case applepay2-1_TW
|  | applepay2-2 |  |  | N/A | Replace by test case applepay2-2_TW
|  | applepay2-3 |  |  | N/A | "IDTECH ENCRYPTION NO card" is not available
|  | applepay3-0 | Set merchant ID1 for IDTECH cards with URL |  | Skip
|  | applepay3-1 |  |  | N/A | Replace by test case applepay3-1_TW
|  | applepay3-2 |  |  | N/A | Replace by test case applepay3-2_TW
|  | applepay3-3 |  |  | N/A | "IDTECH ENCRYPTION NO card" is not available
|  | applepay4 | Set merchant ID2 |  | N/A | "Unencrypted Rewards card" is not available
|  | applepay5 | Set merchant ID4 |  | Skip
|  | applepay6 | Set merchant ID5 |  | Skip
|  | applepay7-0 | Set merchant ID6 for IDTECH cards |  | Skip
|  | applepay7-1 |  |  | Skip
|  | applepay7-2 |  |  | Skip
|  | applepay7-3 |  |  | N/A | "IDTECH ENCRYPTION NO card" is not available
|  | applepay7-4 |  |  | Skip
| Apple VAS_TW | applepay1-1_TW | noMerchantID |  | Skip
|  | applepay1-2_TW |  |  | Skip
|  | applepay1-3_TW |  |  | Skip
|  | applepay1-5_TW |  |  | Skip
|  | applepay2-1_TW | Set merchant ID1 for IDTECH cards |  | Skip
|  | applepay2-2_TW |  |  | Skip
|  | applepay3-1_TW | Set merchant ID1 for IDTECH cards with URL |  | Skip
|  | applepay3-2_TW |  |  | Skip
| CAPK | CAPK-1 | Delete all CAPKs, then Set,Get & Delete 31 CAPKs for VISA RID |  | Skip
|  | CAPK-2 | Set CAPKs for Master RID |  | Skip
|  | CAPK-3 | Ensure enable to set CAPK for 30 RID |  | Skip
|  | CAPK-4 | Delete all VISA CAPKs |  | Skip
|  | CAPK-5 | Error codes (41,44,47,48,49 |  | N/A | Replace by test case CAPK-5_TW
|  | CAPK-5_TW | Error codes (41,44,47,48,49 |  | Skip
| DS | DS-0 | Set dataset with minimum and maxmum value |  | Skip
|  | DS-1 | Get all default datasets |  | Skip
|  | DS-2 | Delete datasets (datasets used by system AID can't be deleted) |  | Skip
|  | DS-3 | Delete datasets after deleting system AIDs |  | N/A | Replace by test case DS-3_TW
|  | DS-3_TW | Delete datasets after deleting system AIDs |  | Skip
|  | DS-4 | Reset datasets deleted in DS-3 then get to ensure |  | Skip
|  | DS-5.1 | DFEE35 | qVSDC 36 | Skip
|  | DS-5.2 |  |  | Skip
|  | DS-5.3 | DFEE35, FFEE12 |  | Skip
|  | DS-5.4 | DFEE35, FFEE13 |  | Skip
|  | DS-5.5 | DFEE35, FFEE17 | qVSDC 18 | Skip
|  | DS-5.6 | DFEE35 | qVSDC 36 | Skip
|  | DS-6 | DFEE39 | Master MS & M-Chip | N/A | Replace by test case DS-6_TW
|  | DS-6_TW | DF811B | Master MS & M-Chip | Skip
Contactless/ PassThrough | CardType | CTP-CommandCanOnlyUseInPT | CommandCanOnlyUseInPT |  | Skip
|  | CTP-CheckTimeOut | CheckTimeOut |  | Skip
|  | CardType-PollForCardEnableAntenna | PollForCardEnableAntenna | Type 1,2,3,4,7 | Skip
|  | CardType-PollForCardDisableAntenna | PollForCardDisableAntenna |  | Skip
| EnhancedCardType | ECTP-CommandCanOnlyUseInPT | CommandCanOnlyUseInPT |  | Skip
|  | ECTP-CantP4TWithCLFlagOff | CantP4TWithCLFlagOff |  | Skip
|  | ECTP-CheckTimeOut | CheckTimeOut |  | Skip
|  | ECTP-PollForCard | Poll for card | Type 1,2,3,7 | Skip
| E-purse | EP-0 | Ensure related commands can only use in PT mode | Mifare S70 | Skip
|  | EP-1 | Test E-purse command with or without backup |  | Skip
|  | EP-2 |  |  | N/A | Replace by EP-2_TW
|  | EP-2_TW |  |  | Skip
|  | EP-3 |  |  | Skip
|  | EP-4 |  |  | Skip
|  | EP-5 | Test with block 32-34 |  | Skip
| Mifare | Mifare-MifareCommandsCanOnlyUseInPT | MifareCommandsCanOnlyUseInPT | Mifare S50 | Skip
|  | Mifare-ReadAllBlocksOneByOne | ReadAllBlocksOneByOne |  | N/A | Replace by Mifare-WriteAllDataBlocksOneByOne+Read16OneTime_TW
|  | Mifare-ReadAllBlocksOneByOne_TW | ReadAllBlocksOneByOne |  | Skip
|  | Mifare-ReadFailWhenAuthFail | ReadFailWhenAuthFail |  | Skip
|  | Mifare-Write3BlocksOnce+Read3BlocksOnce | Write3BlocksOnce+Read3BlocksOnce |  | Skip
|  | Mifare-WriteAllDataBlocksOneByOne+Read16OneTime | WriteAllDataBlocksOneByOne+Read16OneTime |  | N/A | Replace by Mifare-WriteAllDataBlocksOneByOne+Read16OneTime_TW
|  | Mifare-WriteAllDataBlocksOneByOne+Read16OneTime_TW | WriteAllDataBlocksOneByOne+Read16OneTime |  | Skip
|  | Mifare-WriteWrongLengthData | WriteWrongLengthData |  | Skip
| PCD Exchange | PCD-PCDCommandCanOnlyUseInPT | PCDCommandCanOnlyUseInPT | Mifare S70 | Skip
|  | PCD-WriteReadBlock1 | WriteReadBlock1 |  | N/A | Replace by PCD-WriteReadBlock1_TW
|  | PCD-WriteReadBlock1_TW | WriteReadBlock1 |  | Skip
|  | PCD-WriteReadBlock5 | WriteReadBlock5 |  | Skip
|  | PCD-AuthFailWithWrongKey | AuthFailWithWrongKey |  | Skip
|  | PCD-WriteReadBlock5FailAfterAuthSector0 | WriteReadBlock5FailAfterAuthSector0 |  | N/A | Refer to AR 3.0.0 IDG document rev 82
|  | PCD-WriteReadBlock6FailWithWrongDataLength | WriteReadBlock6FailWithWrongDataLength |  | Skip
|  | PCD-WriteReadFailWithoutAuth | WriteReadFailWithoutAuth |  | N/A | Refer to AR 3.0.0 IDG document rev 82
| ULTR | ULTR-1 | Read & write Mifare Ultralight C card | Mifare Ultralight C | Skip
|  | ULTR-2 |  |  | Skip
Note on G143: Kate-Hung: Refer to the description of CMD 2C-06 in AR 3.0.0 IDG rev 82 Once a block has been successfully authenticated, reads and writes to blocks using the same key can be performed without authenticating each block.
Note on G145: Kate-Hung: Refer to the description of CMD 2C-06 in AR 3.0.0 IDG rev 82 Once a block has been successfully authenticated, reads and writes to blocks using the same key can be performed without authenticating each block.

## Diagnostic
Part | Title | Title No. | Case No./Name | Description | Test result | JIRA | Duc Note
Diag | Ping | 01Ping | FWI00101 | Ping | Pass |  | Pass on r26188
| Get Firmware Version | 02Get Firmware Version | FWI00201 | Get Firmware Version | Pass |  | Created script for signed builds, Pass on r26188
| Get Processor Type | 03Get Processor Type | FWI00301 | Get Processor Type TLV | Pass |  | Pass on r26188
| Get Module Version | 04Get Module Version | FWI00401 | Get Module Version | Pass |  | Replace by test case FWI00401_TW
| Get Module Version | 04Get Module Version | FWI00401_TW | Get Module Version | Pass |  | Pass on r26188, Fixed script for Pisces
| Serial Number | 05Serial Number | FWI00501 | Get and Set Serial Number | Pass |  | Pass on r26188, use manuafacter tool to clear SN
| Get Memory Status | 06Memory Status | FWI00601 | Get Memory Status | Pass |  | Pass on r26188, Fix script
| MAC Address | 07MAC Address | FWI00701 | Set MAC Address | Pass |  | Pass on r26188, Fix script for 0A instead of 05 error response
| Reboot | 08Reboot | FWI00801 | Reboot | Pass |  | Pass on r26188

## EMV-CMD
Part | Title | Title No. | Case No./Name | Description | Test result | JIRA | Duc Note
EMV-CMD | EMV Transaction Log | - | EMVTransactionLog | EMV Transaction Log | Skip |  | Not to run w/ this script
| EMV Certificate Revocation List | - | EMVCertificateRevocationList | EMV Certificate Revocation List | Pass |  | All tests pass on r26188
| EMV Exception List | - | EMVCertificateExceptionList | EMV Certificate Exception List | Pass |  | All tests pass on r26188

## Event
Part | Title | Title No. | Case No./Name | Description | Test result | JIRA | Duc Note
Event | Get Input Event | FW.D.001 | FWD00101 | Button Event | Pass |  | All tests pass on r26188, Click buttons on screen
|  |  | FWD00102 | Checkbox Event | Pass |  | All tests pass on r26188, Click checkbox on screen
|  |  | FWD00103 | Line Item Event | Pass |  | All tests pass on r26188. Updated latest Docklight Script, rs232 connection, View items on screen
|  |  | FWD00104 | Keypad Event | Pass |  | All tests pass on r26188, Get input event, automatic pass
|  |  | FWD00105 | Touchscreen Event | Skip |  | Not to run w/ this script
|  |  | FWD00106 | Slideshow Event | Pass |  | All tests pass on r26188, automatic pass
|  |  | FWD00107 | Transaction Event | N/A |  | Not for Secure unit
|  |  | FWD00108 | Radio button event | Pass |  | All tests pass on r26188. Updated latest Docklight Script, rs232 connection, radio button checkbox on screen
|  |  | FWD00109 | Timeout Test | N/A |  | Replace by test case FWD00109_TW
|  |  | FWD00109_TW | Timeout Test | Pass |  | All tests pass on r26188, automatic pass
| Clear Event Queue | FW.D.002 | FWD00201 | Clear Event Queue | Pass |  | All tests pass on r26188, automatic pass

## Pass-Thru
Part | Title | Title No. | Case No./Name | Description | Test result | Duc Note | Jira
Pass-Thru | Start&Stop Pass-Through | FW.F.001.Start&Stop Pass-Through | FWF00101 | Pass-Through operation procedure | Pass | All test pass on r26188, Updated latest Docklight Script, Automatic pass
|  |  | FWF00102 | whether pass-through mode block non-pass-thru command | Pass | All test pass on r26188, Updated latest Docklight Script, Automatic pass
|  |  | FWF00103 | whether pass-through mode exits after device reboot | Pass | All test pass on r26188. Updated latest Docklight Script, reboot manually, then pass automatically
|  |  | FWF00104 | Wrong format check | Pass | All test pass on r26188, Updated latest Docklight Script, Automatic pass
| Control LED | FW.F.002.Control LED | FWF00201 | Pass-Through mode control LED | Pass | All test pass on r26188. Updated latest Docklight Script, Verify LED | See PSH-885 Fixed and Closed
|  |  | FWF00202 | Check whether work in non-pass-thru mode | Pass | All test pass on r26188. Updated latest Docklight Script, Verify LED
|  |  | FWF00203 | Wrong format check | Pass | All test pass on r26188. Updated latest Docklight Script, Verify LED
| Control Buzzer | FW.F.003.Control Buzzer | FWF00301 | Pass-Through mode control buzzer | Pass | All test pass on r26188. Updated latest Docklight Script, Verify buzzer
|  |  | FWF00302 | Check whether work in non-pass-thru mode | Pass | All test pass on r26188. Updated latest Docklight Script, Verify buzzer
|  |  | FWF00303 | Wrong format check | Pass | All test pass on r26188. Updated latest Docklight Script, Verify buzzer
| Enhanced Pass-Through | FW.F.004.Enhanced Pass-Through | FWF00401 | Timeout | Pass | All test passes. Updated latest Docklight Script, Automatic pass.
|  |  | FWF00402 | Transaction Flags | Fail | Fail r26188 with Docklight, tap and insert card, Kate Can you run this? | PSH-885 Fixed and Closed
|  |  | FWF00403 | Contact Interface to Use | Fail | Fail r26188 with Docklight, tap and insert card, Kate Can you run this? | PSH-843 - Fixed and Closed
|  |  | FWF00404 | Buzz | Pass | All test pass on r26188. Updated latest Docklight Script, Observe PT buzzer
|  |  | FWF00405 | LED | Pass | All test pass on r26188. Updated latest Docklight Script, Observe LEDs
|  |  | FWF00406 | Display String | Pass | All test pass on r26134. Modified script to display correct 2nd string, Rerun again if not all test pass on first run | PSH-954 -Not a bug
| Get ATR | FW.F.005.Get ATR | FW.F.005.01/ 1-1GetATR_ICC_2C-12 | Get ATR | Fail/INV | GET ATR (ICC Slot) Fail - Do not have card (80005206-001) | Kate can you run this?
|  |  | FW.F.005.01/ 1-2GetATR_SAM1_2C-12 |  | Fail/INV | GET ATR (SAM1 Slot) & Enhanced PT, Deactivate Fail - Investigate | Kate Can you run this?
|  |  | FW.F.005.01/ 1-3GetATR_SAM2_2C-12 |  | Fail/INV | GET ATR (SAM2 Slot) & Enhanced PT, Deactivate Fail - Investigate | Kate Can you run this?
|  |  | FW.F.005.01/ 1-4GetATR_SAM3_2C-12 |  | Fail/INV | GET ATR (SAM2 Slot) & Enhanced PT, Deactivate Fail - Investigate | Kate Can you run this?
| Exchange APDU | FW.F.006 Exchange APDU | 1ExchangeAPDU_ICC_2C-13 | Exchange APDU for ICC/SAM | Fail/INV | 5 test failed - Investigate, Do not have card (80005206-001) | Kate Can you run this?
Note on H6: Duc: Observed on r26024
Note on G17: Duc: reset to default before running script.

## Secure Passthrough
Part | Title | Title No. | Case No./Name | Description | Test result | Notes
Secure Passthrough | - | - | PassThrough_ExchangeCLData_WithWhitelist_2C-03 | - | Skip
| - | - | PassThrough_ExchangeCLData_WithWhitelist_2C-13_TW | - | Fail | See failed tests and results below on r26188. Kate can you run these since there are many failures?
[5 empty] | Fail | SMFG Set White List returns 91 0A, expecting 91 00
[5 empty] | Fail | UMFG Device Reset returns 90 0A, expecting 90 00
[5 empty] | Fail | Set Serial Number returns 90 07, expecting 90 00
[5 empty] | Fail | UMFG Set UTC returns 90 0A, expecting 90 00
[5 empty] | Fail | UMFG Activate returns 90 0A, expecting 90 00
[5 empty] | Fail | Load Certificates returns 90 0A, expecting 90 00
[5 empty] | Fail | UMFG Validate Certificate Tree returns 90 0A, expecting 90 00
[5 empty] | Fail | UMFG Lock returns 90 0A, expecting 90 00
[5 empty] | Fail | UMFG Device Reset returns 90 0A, expecting 90 00
[5 empty] | Fail | Set Serial Number returns 90 07, expecting 90 00
[5 empty] | Fail | UMFG Set UTC returns 90 0A, expecting 90 00
[5 empty] | Fail | UMFG Activate returns 90 0A, expecting 90 00
[5 empty] | Fail | Load Certificates returns 90 0A, expecting 90 00
[5 empty] | Fail | UMFG Validate Certificate Tree returns 90 0A, expecting 90 00
[5 empty] | Fail | UMFG Lock returns 90 0A, expecting 90 00
[5 empty] | Fail | SMFG Clears White List returns 90 0A, expecting 90 00
[5 empty] | Fail | SMFG Master Reset returns 91 0A, expecting 91 00
[5 empty] | Fail | Load KEK returns 02 06 00 15 90 57 78 46 F2 1E AC 03, expecting 06 78 46 F2 03 00 5B AE 0A
[5 empty] | Fail | SMFG Delete All Keys returns 91 0A, expecting 91 00
[5 empty] | Fail | KEK5300 returns 02 06 00 15 90 57 78 46 F2 1E AC 03, expecting 06 78 46 F2 03 00 5B AE 0A
[5 empty] | Fail | KEK6300 returns 02 06 00 15 90 57 78 46 F2 1E AC 03, expecting 06 78 46 F2 03 00 5B AE 0A
[5 empty] | Fail | Set to Default, no response.
[5 empty] | Fail | Enable Mac returns 81 0B, expecting 81 00
[5 empty] | Fail | Swipe Card returns 02 03, expecting 56 69 56 4F 74 65 63 68 32 00 02 00 "Change AT to 02 05 instead of 02 40"????
[5 empty] | Fail | PPSE returns 2C 0A, expecting 2C 00 ** ** etc.
[5 empty] | Fail | Select AID return 2C 0A, expecting 2C 00 ** ** etc
[5 empty] | Fail | GPO -Contain57 returns 2C 0A, expecting 2C 00 ** ** etc.
[5 empty] | Fail | Read Record SFI1-Recore1 returns 2C 0C, expecting 2C 00 ** ** etc.
[5 empty] | Fail | Read Record SFI1-Recore2 returns no response, expecting 2C 00
[5 empty] | Fail | Read Record SFI2-Record1 -ContainPAN returns returns 2C 0C, expecting 2C 00 , expecting 70 10 5A 08 47 61 73 90 01 01 00 10 5F 24 03 20 12 31 90 00
[5 empty] | Fail | Read Record SFI2-Record2 returns 2C 0C, expecting 70 0A 9F 69 07 01 11 22 33 44 20 00 90 00

## Transaction
Part | Title | Title No. | Case No./Name | Description | Test result | Note | Jira
| New MSR Transaction | 01MSRTrans | MSRTrans_FallbackFlag_02-05 | Fallback flag | Investigate | All test fail on r26188 with USB. Shows pass on rs232 but does not look correct. Kate, can you check on your side? Check w v25375 fw | PSH-778 - Old/Closed
|  |  | MSRTrans_MSRIFlag_02-05 | MSR Interface flag | Pass | All test pass on r26188, Swipe magstripe to ensure does not work.
|  |  | MSRTrans_Event_02-05 | Event Mode | Fail | Test fail on r26188 on both rs232 and usb. Kate can you check this on your side? Pass on r26134
| ICC Transaction | FW.E.002 | FWE00201/ ICCTrans_TLV9F02 | Amount 9F02, Secure | N/A | Replace by test case FWE00201/ICCTrans_TLV9F02_TW
|  |  | FWE00202/ ICCTrans_TLV5F2A_02-05 | Transaction Currency Code 5F2A, Secure | N/A | PISCES doesn't support CNY currency character on LCD
|  |  | FWE00203/ ICCTrans_TLV9F1A_02-05 | Terminal Country Code 9F1A, Secure | N/A | Replace by test case FWE00203/ICCTrans_TLV9F1A_02-05_TW
|  |  | FWE00204/ ICCTrans_TLV9C_02-05 | Transaction Type 9C, Secure | N/A | Replace by test case FWE00204/ICCTrans_TLV9C_02-05_TW
|  |  | FWE00205/ ICCTrans_TLV9F03_02-05 | Amount Other 9F03, Secure | N/A | Replace by test case FWE00205/ICCTrans_TLV9F03_02-05_TW
|  |  | FWE00206/ ICCTrans_TLVDFEE0D_02-05 | Force Transaction Online DFEE0D, Secure | N/A | Replace by test case FWE00206/ICCTrans_TLVDFEE0D_02-05_TW
|  |  | FWE00207/ ICCTrans_TLVDFEE11_02-05 | Transaction Logging DFEE11, Secure | N/A | Replace by test case FWE00207/ICCTrans_TLVDFEE11_02-05
|  |  | FWE00211/ ICCTrans_TLV5F36_02-05 | Transaction Currency Exponent 5F36, Secure | N/A | Replace by test case FWE00211/ICCTrans_TLV5F36_02-05_TW
|  |  | FWE00213/ ICCTrans_TLVDFEF1F_02-05 | Auto Authenticate DFEF1F, Secure | N/A | Replace by test case FWE00213/ICCTrans_TLVDFEF1F_02-05_TW
|  |  | FWE00214/ ICCTrans_TLVDFEE1A_02-05 | Output data element DFEE1A, Secure | N/A | Replace by test case FWE00214/ICCTrans_TLVDFEE1A_02-05_TW
|  |  | FWE00201/ICCTrans_TLV9F02_TW | Amount 9F02, Secure | Pass | All test pass on r26188. Don't have card "(V2CM0940002v4.3f)" but still passes
|  |  | FWE00203/ICCTrans_TLV9F1A_02-05_TW | Terminal Country Code 9F1A, Secure | Pass | All test pass on r26188 . Don't have card "(V2CM0940002v4.3f)" but still passes
|  |  | FWE00204/ICCTrans_TLV9C_02-05_TW | Transaction Type 9C, Secure | Pass | All test pass on r26188 . Don't have card "(V2CM0940002v4.3f)" but still passes
|  |  | FWE00205/ICCTrans_TLV9F03_02-05_TW | Amount Other 9F03, Secure | Pass | All test pass on r26188 . Don't have card "(V2CM0940002v4.3f)" but still passes
|  |  | FWE00206/ICCTrans_TLVDFEE0D_02-05_TW | Force Transaction Online DFEE0D, Secure | Investigate | All test pass on r26188 w rs232 and 1 failed with USB on r26188 (2nd test). Don't have card "(V2CM0940002v4.3f)"
|  |  | FWE00207/ICCTrans_TLVDFEE11_02-05_TW | Transaction Logging DFEE11, Secure | Pass | All test pass on r26188. Don't have card "(V2CM0940002v4.3f)" but still passes
|  |  | FWE00211/ICCTrans_TLV5F36_02-05_TW | Transaction Currency Exponent 5F36, Secure | Pass | All test pass on r26188. Don't have card "(V2CM0940002v4.3f)" but still passes
|  |  | FWE00213/ICCTrans_TLVDFEF1F_02-05_TW | Auto Authenticate DFEF1F, Secure | Investigate | All test pass on r26188 w rs232 and 1 failed with USB on r26188 (1st test). Don't have card "(V2CM0940002v4.3f)"
|  |  | FWE00214/ICCTrans_TLVDFEE1A_02-05_TW | Output data element DFEE1A, Secure | Pass | All test pass on r26188. Don't have card "(V2CM0940002v4.3f)" but still passes
| Transaction Command Properties | FW.E.003 | FWE00301/ FWE00301C | Timeout, Secure | N/A | Due to the timeout value 0x00 is not prohibit in AR IDG, this test case is not available (Refer to AR 3.0.0 IDG rev 82)
|  |  | FWE00302/FWE00302C-01 | UI Flags, Secure | Pass | All test pass on r26188, Check top line font and color
|  |  | FWE00302/FWE00302C-02 |  | Pass | All test pass on r26188, Check bottom line font and color
|  |  | FWE00302/FWE00302C-03 |  | N/A | Replace by test case FWE00214/ICCTrans_TLVDFEE1A_02-05_TW
|  |  | FWE00302/FWE00302C-03_TW |  | Pass | All test pass on r26188, Check top and bottom line font and color
|  |  | FWE00303/FWE00303 | Cancel Transaction | Partial Pass | Pass 1st test, Do not have JCB Retail terminal card for 2nd test, Kate Can you run this?
|  |  | FWE00304/FWE00304 | Stop Transaction | Pass | All test pass on r26188, Stop Transaction
| Prompt Credit/Debit | FW.E.005 | FWE00501 | Timeout | Investigate | All test pass on r26188 w rs232 and fail with USB. Kate, can you check on your side?
|  |  | FWE00502 | Currency character | Pass | All test pass on r26188, rerun test 1 on USB multiple times to show pass
|  |  | FWE00503 | Display string | Investigate | All test pass on r26188 w rs232 and 1 failed with USB on r26188 (1st test)
|  |  | FWE00504 | Displayed Button Response | Pass | All test pass on r26134, Fail on r26188, only credi and debit buttons work. Now others buttons work next day | PSH-997 - Not a bug, Closed
| Get Online Enciphered PIN | FW.E.006 | FWE00601/FWE00601-AES | Timeout | Fail | 4 of 5 test failed on r26188. Returns 83 43 0A instead of 83 43 08, Modified script for timeout response | PSH-998 - New
|  |  | FWE00601/FWE00601-TDES |  | Pass | All pass on r26188, modified script for timeout response and error code. 5-14-20
|  |  | FWE00602/FWE00602-AES | PIN block format | Skip | Wait for F/W team to clarify how to use command 83-43 (Get Online Enciphered PIN)
|  |  | FWE00602/FWE00602-TDES |  | Skip

## UI
Part | Title | Title No. | Case No./Name | Description | Test result | Notes | Note | JIRA Tickets | Last Tested Build | JIRA | Notes
| LCD Contrast | 02LCDContrast | LCDcontrast_83-2D,2E | Set and get LCD contrast | N/A | Replace by test case LCDcontrast_83-2D,2E_TW |  |  | 24809
|  |  | LCDcontrast_83-2D,2E_TW | Set and get LCD contrast | Pass | All test pass on r26188
| LCD Backlight | 03LCDBacklight | LCDBacklight_83-2F | Set Backlight | Pass | All test pass on r26134 | Invalid value is not blocked | PSH-512 | 24809
|  |  | LCDBacklight_83-2F_TW | Set Backlight | Pass | All test pass on r26188
| Foreground and Background Color | 04FGBGColor | FGBGColor_83-0A | Set foreground and background Color | Pass | All test pass on r26134 | Invalid value is not blocked |  | 24809
|  |  | FGBGColor_83-0A_TW | Set foreground and background Color | Pass | All test pass on r26188 | Invalid value is not blocked |  | 24809
| Display Rectangle | 05Rectangle | 1Rectangle_Coodinate_83-0F | Display Rectangle in different colors | N/A | Replace by test case 1Rectangle_Coodinate_83-0F_TW | allow out of screen |  | 24809
|  |  | 1Rectangle_Coodinate_83-0F_TW | Display Rectangle in different colors | Pass | All test pass on r26188
|  |  | 2Rectangle_Size_83-0F | Display Rectangle in different positions | N/A | Replace by test case 2Rectangle_Size_83-0F_TW | allow out of screen |  | 24809
|  |  | 2Rectangle_Size_83-0F_TW | Display Rectangle in different positions | Pass | All test pass on r26188 | allow out of screen |  | 24809
|  |  | 3Rectangle_Color_83-0F | Display Rectangle in different size | Pass | Replace by test case 3Rectangle_Color_83-0F_TW
|  |  | 3Rectangle_Color_83-0F_TW | Display Rectangle in different size | Pass | All test pass on r26188, Updated script to return 05 instead of 0A per PSH-801 | allow out of screen |  | 24809 | Refer to PSH-801 Fixed and Closed
| Display Button | 06Button | 1Button_Coordinate_83-05 | Coordinate | Pass | Replace by test case 1Button_Coordinate_83-05_TW |  |  | 24809
|  |  | 1Button_Coordinate_83-05_TW | Coordinate | Pass | All test pass on r26188, Updated script to return 0A |  |  |  | PSH-958 Closed/Wont Fix
|  |  | 2Button_Size_83-05 | Size | Pass | Updated script to return 0A |  |  | 24809 | PSH-958 Closed/Wont Fix
|  |  | 2Button_Size_83-05_TW | Size | Pass | All test pass on r26188, Updated script to return 0A |  |  |  | PSH-958 Closed/Wont Fix
|  |  | 3Button_Font_83-05 | Font | N/A | on r26134, 1 test failed - TID:Out of Screen Coordinate[500,500] - Expecting: "05" instead of "0A" |  |  | 24809 | PSH-958 Closed/Wont Fix
|  |  | 3Button_Font_83-05_TW | Font | Pass | All test pass on r26188
|  |  | 4Button_Option_83-05 | Display Option | N/A | Replace by test case 4Button_Option_83-05_TW |  | PSH-513 | 24809
|  |  | 4Button_Option_83-05_TW | Display Option | Pass | All test pass on r26188
|  |  | 5-1Button_StringSecure_83-05 | Custom Buttons | N/A | Replace by test case 5-1Button_StringSecure_83-05_TW |  |  | 24809
|  |  | 5-1Button_StringSecure_83-05_TW | Custom Buttons | Pass | All test pass on r26188, press keypad, no beeps expected
|  |  | 5-2Button_StringSecure_83-05 | Pre-defined Buttons | N/A | Replace by test case 5-2Button_StringSecure_83-05_TW
|  |  | 5-2Button_StringSecure_83-05_TW | Pre-defined Buttons | Pass | All test pass on r26188, press button on lcd
|  |  | 6Button_TextColor_83-05 | Text color | N/A | Replace by test case 6Button_TextColor_83-05_TW | Not match IDG |  | 24809
|  |  | 6Button_TextColor_83-05_TW | Text color | Pass | All test pass on r26188
|  |  | 7Button_BGColor_83-05 | Background color | N/A | Replace by test case 7Button_BGColor_83-05_TW
|  |  | 7Button_BGColor_83-05_TW | Background color | Pass | All test pass on r26188 |  | PSH-164 | 24809
| Display Radio Button | 07RadioButton | 1RadioButton_Coordinate_83-12 | Coordinate | Pass | All test pass on r26188 |  |  | 24809
|  |  | 2RadioButton_Size_83-12 | Size | Pass | All test pass on r26188 |  |  | 24809
|  |  | 3RadioButton_Group_83-12 | Group | Pass | All test pass on r26188 |  |  | 24809
|  |  | 4RadioButton_String_83-12 | String | N/A | All test pass on r26191 | Do not allow no string |  | 24809
|  |  | 4RadioButton_String_83-12_TW | String | Pass | All test pass on r26188
|  |  | 5RadioButton_Font_83-12 | Font | Pass | All test pass on r26188 | Large size font looks not well |  | 24809 | PSH-1001 - New - Radio button display over lapping and under lapping boarder
|  |  | 6RadioButton_Interval_83-12 | Interval | Pass | All test pass on r26188 |  |  | 24809
|  |  | 7RadioButton_Selected_83-12 | Selected Flag | Pass | All test pass on r26188 |  | PSH-514 | 24809
|  |  | 8RadioButton_Exclusiveness_83-12 | Exclusiveness | Pass | All test pass on r26188 |  |  | 24809
| Text | 08Text | 6Text_SecureText_83-03 | Special Secured Text String | N/A | Replace by test case 6Text_SecureText_83-03_TW
|  |  | 6Text_SecureText_83-03_TW | Special Secured Text String | Fail | 1 test failed Change Text to valid Text(please enter zip code)(7) |  |  |  |  | Kate can you run this on your side and see results?
| Amount | 09Amount | 1Amount_Coordinate_83-04 | Coordinate | Pass | All test pass on r26188 |  |  | 24809
|  |  | 2Amount_Size_83-04 | Size | Pass | All test pass on r26188 |  |  | 24809
|  |  | 3Amount_Font_83-04 | Font | Pass | All test pass on r26188 |  |  | 24809
|  |  | 4Amount_Option_83-04 | Display Option | Pass | All test pass on r26188 |  |  | 24809
|  |  | 5Amount_Currency_83-04 | Currency | Pass | All test pass on r26188 |  | PSH-515 | 24809
|  |  | 6Amount_Amount_83-04 | Amount | Pass | All test pass on r26188, Udpated script to change response to 83 04 05 |  |  | 24809 | Refer to PSH-805 - Not a bug
|  |  | 7Amount_ChangeCurrency_83-17 | Change Currency | Pass | All test pass on r26188 |  |  | 24809
|  |  | 8Amount_ChangeAmount_83-17 | Change Amount | Pass | All test pass on r26188 |  |  | 24809
| Display Paragraph | 10Paragraph | 1Paragraph_Coordinate_83-28 | Coordinate | Pass | All test pass on r26188 |  |  | 24809
|  |  | 2Paragraph_Size_83-28 | Size | Pass | All test pass on r26188 |  | VSF-3552 | 24809
|  |  | 3Paragraph_Font_83-28 | Font | Pass | All test pass on r26188 |  |  | 24809
|  |  | 4Paragraph_Option_83-28 | Display Option | Pass | All test pass on r261388, Updated script to change response to correct value | undefined value 36 is allowed |  | 24809 | Refer to PSH-803 Fixed and Closed
|  |  | 5Paragraph_String_83-28 | String | Pass | All test pass on r26188 |  |  | 24809
| Display input field | 12InputField | 1InputField_Size_83-1C | Size | Pass | All test pass on r26188 |  |  | 24809
|  |  | 2InputField_Coordinate_83-1C | Coordinate | Pass | All test pass on r26188 |  |  | 24809
|  |  | 3InputField_Font_83-1C | Font | Pass | All test pass on r26188 |  |  | 24809
|  |  | 4InputField_Option_83-1C | Display option | Pass | All test pass on r26188 |  |  | 24809
|  |  | 5InputField_Color_83-1C | Color | Pass | All test pass on r26188 |  |  | 24809
|  |  | 6InputField_Prefilled_83-1C | Prefilled | Pass | All test pass on r26188, Upadated script |  |  | 24809 | Refer to PSH-865 from Kate - Not a bug
|  |  | 7InputField_Format_83-1C | Format | Pass | All test pass on r26188 |  |  | 24809
|  |  | 8InputField_Get_83-1D | Get Input Field Value | Fail | 1 of 2 test failed - Get Input Field (1) - See note. |  |  | 24809 |  | Kate can you run this on your side and see results?
|  |  | 9InputField_Clear_83-1E | Clear Input Field | Fail | 1 of 2 test failed Clear Input Field (1) - Not cleared - see note. |  |  | 24809 |  | Kate can you run this on your side and see results?
| Signature | 13Signature | 1GetSignature_Timeout_83-02 | Get Signature, Timeout | Pass | All test pass on r26188. Serial connection and USB |  |  | 24809
|  |  | 2GetSignature_Format_83-02 | Get Signature, Format | Fail | All test pass on r26188. USB |  |  | 24809 | PSH-1000 - Get Signature (83-02) does not return to "Welcome" after signature is complete | Kate can you run this on your side and see results?
|  |  | 3StartSignature_Coordinate_83-19 | Start signature, Coordinate | Pass | All test pass on r26188 |  |  | 24809
|  |  | 4StartSignature_Size_83-19 | Start signature, Size | Pass | All test pass on r26188, Updated script to change response to correct value | undefined value 00 is allowed |  | 24809
|  |  | 5StartSignature_Option_83-19 | Start signature, Display option | Pass | All test pass on r26188, Updated script "00 (Do not show anything on LCD)", added test case for "03" | bmp too big |  | 24809
|  |  | 6StartSignature_Format_83-19 | Start signature, Format | Pass | All test pass on r26188 |  |  | 24809
|  |  | 7GetSignCapture_83-1A | Get signature capture data | Pass | 1 of 2 test failed, Get Signature Capture EXR:83 1A 00, |  |  | 24809
|  |  | 8ClearSignCapture_83-1B | Clear signature capture data | Pass | All test pass on r26134, All test pass on r26134, "00 52 19 F8"
| Check Box | 14Checkbox | 1Checkbox_Coordinate_83-18 | Coordinate | Pass | All test pass on r26134 |  |  | 24809
|  |  | 2Checkbox_Size_83-18 | Size | Pass | All test pass on r26134 |  |  | 24809
|  |  | 3Checkbox_State_83-18 | State | Pass | All test pass on r26134 |  |  | 24809
| Directory and File | 15Directory | FWA01501 | List directory | Pass | All test pass on r26134 |  |  | 24809
|  |  | FWA01502 | Create and delete directory and File | Pass | All test pass on r26134 |  |  | 24809
| Free space | 16File and Free Space | FWA01601 | Get Drive Free Space | Pass |  | Free space | PSH-163 | 24809
| Display Image | 17Image | FWA01701A | Coordinate, png | Pass |  |  | PSH-76 | 24809
|  |  | FWA01701A_TW | Coordinate, png | Pass | All test pass on r26134, must transfer image to reader, see notes in script folder |  |  |  | PSH-969 Fixed and Closed | Refer to PSH-808
|  |  | FWA01701B | Coordinate, bmp | Pass | All test pass on r26134, must transfer image to reader, see notes in script folder |  | PSH-76 | 24809 | PSH-969 Fixed and Closed | Refer to PSH-808
|  |  | FWA01702A | Display option, png | Pass/INV | All test pass on r26134, 1st run showed 7 of 19 failed, ran again then pass. |  | PSH-76 | 24809 |  | Kate can you run this on your side and see results?
|  |  | FWA01702B | Display option, bmp | Pass/INV | All test pass on r26134, 1st run showed failures, ran again then pass. |  | PSH-76 | 24809 |  | Kate can you run this on your side and see results?
|  |  | FWA01703 | Different file path | Fail | 4 of 4 failed on r26134, Expecting 83 0E 00 instead of 83 0E 0A, need to detete images and add new image name |  |  | 24809 | PSH-969 Fixed and Closed
| Slideshow | 18Slideshow | FWA01801 | Display slideshow, Coordinate | Pass | All test pass on r26134 | 超出范围后允许显示但效果不佳 |  | 24809
|  |  | FWA01802 | Display slideshow, Display option | Pass | All test pass on r26134 | 不清屏参数无效，touch sensitive需要83 06激活触摸屏 |  | 24809
|  |  | FWA01803 | Display slideshow, Interval time | Pass | All test pass on r26134 |  |  | 24809
|  |  | FWA01804 | Display slideshow, Ioop | Pass | All test pass on r26134 |  |  | 24809
|  |  | FWA01806 | Stop slideshow | Pass | All test pass on r26134 |  |  | 24809
| Set property | 19Set Property | FWA01901 | Set touch property | Pass | All test pass on r26134, 01 48 9A 28 | not available for list item |  | 24809
Note on G13: Duc: Expecting: "0A" instead of "05" CMD:83 0F 30 00 30 00 35 30 00 35 30 00 30 30 30 30 30 30 67 67 00 00 00 E_CODE: 0A Actual: TX:56 69 56 4F 70 61 79 56 33 00 83 0F 00 15 30 00 30 00 35 30 00 35 30 00 30 30 30 30 30 30 67 67 00 00 00 C8 F7 RX:56 69 56 4F 70 61 79 56 33 00 83 0F 05 00 00 18 86
Note on G46: 2 of 8 tests failed, Expecting response 83 04 00, received 83 04 05. Same previous DVT'd r26024.
Note on G61: Duc: TID:Get Input Field (1) CMD:83 1D ?? ?? ?? ?? EXR:31 32 33 34 35 36 37 38 39 30 actual: Get Input Field (1) TX:56 69 56 4F 70 61 79 56 33 00 83 1D 00 00 86 90 RX:56 69 56 4F 70 61 79 56 33 00 83 1D 05 00 00 EE 49
Note on G62: Duc: TID:Clear Input Field (1) CMD:83 1E ?? ?? ?? ?? EXR:83 1E 00 Clear Input Field (1) TX:56 69 56 4F 70 61 79 56 33 00 83 1E 00 00 D6 C9 RX:56 69 56 4F 70 61 79 56 33 00 83 1E 05 00 00 75 95
Note on G80: Duc: 7 of 19 failed on r26134, Expecting 83 0E 00 instead of 83 0E 0A, Check previous DVT'd r26024
Note on G88: Duc: All test pass on r26024: replace ?? With 01 5B B9 F8

## TS
S/W version:
Product | Interface | Language | Operation mode | P/N | Test result
PISCES | RS232 | Chinese | Production mode
QC mode
|  | English | Production mode
QC mode
| USB HID | Chinese | Production mode
QC mode
|  | English | Production mode
QC mode
P/N | Interface | MSR test in QC mode
IDPP-1381 | RS232 | N/A
IDPP-1381D | RS232 | Yes
IDPP-1581 | USB HID | N/A
IDPP-1581D | USB HID | Yes
IDPP-1881 | USB HID | N/A
IDPP-1881D | USB HID | Yes
IDPP-1881-U1 | USB HID | N/A
IDPP-1881D-U1 | USB HID | N/A
IDPP-1X81X | RS232 USB HID | Yes

## SDK
SDK | ARENA P/N | Version | Interface | PC/Android/iOS ver. | Test result
UniversalSDKDemo