## Sheet1
VPSDK FW Issue List
Issue Number | SDK API to which the issue is related | Corresponding IDG command | Issue type | Issue description | Severity | Status
1 | SIG_DisplayCustomControl | Start Signature Capture (83-19) | FW Bug | When we specify the X and Y coordinates as large value (eg: X=600, Y=600), device sends SUCCESS without actually drawing the signature control in the display. | Major | Open
2 | SIG_DisplayCustomControl | Start Signature Capture (83-19) | FW Bug | When we specify the Width and Height as large value (eg: Width=800, Height=800), device sends SUCCESS and the signature control is drawn exceeding the boundaries of the display. | Major | Open
3 | SIG_DisplayCustomControl | Start Signature Capture (83-19) | FW Bug | When we draw two signature controls overlapped on the same locationof the display, device returns SUCCESS instead of indicating a 'control overlap' error. | Major | Open
4 | SIG_GetCustomControlData | Get Signature Capture Data (83-1A) | FW Bug | Device returns SUCCESS even if we specify an invalid control ID for this IDG command. | Major | Open
5 | SIG_Clear | Clear Signature Capture (83-1B) | FW Bug | Device returns SUCCESS even if we specify an invalid control ID for this IDG command. Further, regardless of the the control ID we specify the signature control drawn in the VP8800 display gets cleared. Following FW bug was also noticed, 1. Draw signature control. 2. Clear display. 3. Issue 'Clear Signature Capture' with any control ID => Here the previously drawn signature controls pops back to visibilty. | Major | Open
6 | GUI_EnableTouchSensitivity | Set Property (83-0B) | FW Bug | This command returns with Failed/Nack for Checkbox conrol | Major | Open
7 | SIG_DisplayBuiltInScreen SIG_DisplayCustomControl | Get Signature (83-02) Start Signature Capture (83-19) | FW Bug | In USB HID mode PNG/BMP formats always sending about 4kB bytes even packet length itself says it is > 4kB. | Major | Open
8 | System_CancelTransaction | Cancel Transaction (05-01) | FW Bug | Cancel Transaction does not cancel pending activate transaction in USB HID mode. | Major | Open