## Sheet1
VPSDK FW Issue List
Issue Number | SDK API to which the issue is related | Corresponding IDG command | Issue type | Issue description | Severity | Status
1 | SIG_DisplayCustomControl | Start Signature Capture (83-19) | FW Bug | When we specify the X and Y coordinates as large value (eg: X=600, Y=600), device sends SUCCESS without actually drawing the signature control in the display. | Major | Open
2 | SIG_DisplayCustomControl | Start Signature Capture (83-19) | FW Bug | When we specify the Width and Height as large value (eg: Width=800, Height=800), device sends SUCCESS and the signature control is drawn exceeding the boundaries of the display. | Major | Open
3 | SIG_DisplayCustomControl | Start Signature Capture (83-19) | FW Bug | When we draw two signature controls overlapped on the same locationof the display, device returns SUCCESS instead of indicating a 'control overlap' error. | Major | Open
4 | SIG_GetCustomControlData | Get Signature Capture Data (83-1A) | FW Bug | Device returns SUCCESS even if we specify an invalid control ID for this IDG command. | Major | Open
5 | SIG_Clear | Clear Signature Capture (83-1B) | FW Bug | Device returns SUCCESS even if we specify an invalid control ID for this IDG command. Further, regardless of the the control ID we specify the signature control drawn in the VP8800 display gets cleared. Following FW bug was also noticed, 1. Draw signature control. 2. Clear display. 3. Issue 'Clear Signature Capture' with any control ID => Here the previously drawn signature controls pops back to visibilty. | Major | Open
6 | GUI_EnableTouchSensitivity | Set Property (83-0B) | FW Bug | This command returns with Failed/Nack for Checkbox conrol | Major | Open
7 | SIG_DisplayBuiltInScreen SIG_DisplayCustomControl | Get Signature (83-02) Start Signature Capture (83-19) | FW Bug | In USB HID mode PNG/BMP formats always sending about 4kB bytes even packet length itself says it is > 4kB. | Major | Open
8 | System_CancelTransaction | Cancel Transaction (05-01) | FW Bug | Cancel Transaction does not cancel pending activate transaction in USB HID mode. | Major | Open
9 | GUI_DisplayCheckBox | Display Check Box (83-18) | FW Bug | This command does not set the background color of the checkbox control area eventhough the user sends a Set Foreground/Background Color (83-0A) command prior to sending this command. This is contradictory to the behaviour of other GUI controls such as buttons, textboxes, amountboxes etc. | Medium | Open
10 | List_AddItem | Add Item to List (83-11) | FW Bug | Sometimes the item is not displayed as the selected item even if the command is sent properly. It was observed that if the command is sent with indicating to select the item for the first item adding to the list, it is always displayed as selected. But there after the items are not displayed as selected even though the command is sent properly to the device. | Medium | Open
11 | Inputfield_Create | Create Input Field (83-1C) | FW Bug | No use of width and height parameters of the IDG command. Eventhough the required height and width are sent in the command, the input box is always resized according to the font size and the number of characters displayed. | Medium | Open
12 | SIG_DisplayBuiltInScreen | Get Signature (83-02) | FW Bug | When the device connection is made through HID and this command is issued with signature type as 'bitmap', the device only sents a maximum of 4096 bytes where it is indicating a larger length in the response | Major | Open